## Architecture Decisions
Key Decision | Options | Implications / Rationale | Decision
Channel architecture for user access | Web and Mobile ; Separate Web and Mobile channels | Different user personas require device optimized UX and accessibility. | Use EPMS Web Portal (React) and EPMS Mobile App (React Native).
User experience technology choice | Native mobile + separate web stack; React + React Native; Low‑code | Shared development patterns and faster delivery using a common ecosystem. | Adopt React for Web and React Native for Mobile.
Internet‑facing security boundary | Direct public access DMZ with CDN/Proxy/Gateway VPN only | Layered security improves protection, scalability and traffic control. | Use DMZ with CDN, Reverse Proxy/LB and API Gateway.
API exposure model | Expose services directly; API Gateway; BFF only | Gateway centralizes throttling, security policy and routing. | All north‑south APIs go through API Gateway.
Authentication & identity | Custom identity; Azure AD; Social login | Enterprise IAM integration needed for SSO, governance and lifecycle. | Use Azure AD with JWT propagation.
Backend for frontend strategy | Direct UI to microservices; Shared backend; Web BFF + Mobile BFF | Channel‑specific orchestration improves flexibility. | Use Web BFF and Mobile BFF.
Business capability decomposition | Monolith; Domain microservices; Workflow‑only system | Domains like Ideation, Campaign, WBS naturally align to microservices. | Use domain‑driven Biz Microservices.
Workflow execution | Hard‑coded workflows; Journey orchestrator; Manual workflow | Long‑running processes require centralized orchestration. | Use Journey Orchestrator.
Business rule management | Rules in code; Rule engine; DB rule tables | Rules change frequently and should be configurable. | Use a dedicated Rule Engine.
Caching strategy | No caching; In‑process cache; Dedicated caching layer | Caching Reduces latency and backend load. | Use centralized caching.
External system integration | Point‑to‑point; Adapter microservices; ESB only | Adapters isolate external dependencies and protocols. | Use Adapter Microservices.
Persistence architecture | Single RDBMS; NoSQL only; Polyglot persistence | Different workloads require different storage types. | Use RDBMS + NoSQL.
Document storage | Store in DB; Document repository; File share | Project artifacts require lifecycle and metadata management. | Use Document Repository.
Enterprise reporting | Operational DB queries; Enterprise data platform; Embedded reporting | Separation prevents operational DB overload. | Use Enterprise Data Platform / BI.
Search capability | DB search; Dedicated search service; Repository search only | Enterprise‑wide search requires indexing and ranking. | Use Search Service.
Event communication | Synchronous only; Event messaging; Batch only | Async messaging decouples services and supports workflows. | Use Event Messaging Platform.
Service networking | Basic HTTP; Service mesh; Message only | Service mesh improves resilience, telemetry and traffic control. | Use Istio Service Mesh.
Observability | Service logs only; Central monitoring; Manual ops | Central observability needed for incident response. | Use Monitoring & Automation with Incident integration.
Deployment model | Manual deployments; CI/CD DevOps; Release trains | Automation improves consistency and speed. | Use DevOps pipelines.
Backup strategy | Ad‑hoc backups; Central backup service; Storage snapshots only | Structured disaster recovery required. | Use centralized backup solution.
Security operations | App team security; Central security monitoring; Periodic audit | Enterprise platform requires vulnerability and endpoint monitoring. | Use centralized security operations.
GenAI placement | Embed AI in services; UI → LLM; Central AI platform | Centralization improves governance and reuse. | Use centralized Enterprise AI Platform.
GenAI interaction pattern | Chatbot only; Read‑only copilot first; Fully autonomous agents | Gradual adoption reduces risk. | Start with read‑only and assistive GenAI.
AI answer source | LLM memory; Vector DB; Systems of record | Operational data must come from authoritative services. | Use EPMS systems of record with AI summarization.
Retrieval architecture | No retrieval; Document RAG; Hybrid retrieval | Queries require structured + unstructured data. | Use hybrid retrieval.
AI tool integration | Direct DB access; Direct microservice calls; Controlled tool layer | Controlled tools ensure security and governance. | Use tool adapter/MCP layer.
Vector database use | No vector DB; Vector DB for RAG; Search engine only | Semantic retrieval improves document Q&A. | Use vector DB for embeddings and semantic search.
Prompt management | Hardcoded prompts; Central prompt store; Ad hoc prompts | Central control ensures consistency and governance. | Use Prompt & Policy store.
AI guardrails | None; App checks; Dedicated guardrail layer | Prevents data leakage and unsafe responses. | Use AI guardrails layer.
AI write‑back control | Autonomous writes; Human approval; Mixed model | Sensitive operations require human oversight. | Require human approval for write actions.
Rule validation for AI | LLM validation; Rule engine validation; Post validation | Deterministic compliance is required. | LLM proposes, Rule Engine validates.
AI observability | Minimal logs; AI audit trail; Vendor logs only | Traceability needed for compliance. | Maintain centralized AI audit logs.
Access control in AI retrieval | Broad access; Respect ACL; Separate AI repo | AI must respect original data permissions. | Propagate user ACL into retrieval.
AI rollout strategy | Big bang; Phased rollout; Pilot only | Controlled adoption minimizes risk. | Adopt phased rollout of GenAI capabilities.